## GANT
VISUAL |  |  |  |  | MVP PITCH | BETA REBUILD |  |  | VIDEO | BREAK |  | FINAL RELEASE |  | CODE |  |  |  |  | MVP PITCH | BETA REBUILD |  |  | VIDEO | BREAK |  | FINAL RELEASE
| 30th Jan | 6th Feb | 13th Feb | 20th Feb | 6th March | 13th March | 20th March | 27th march | 3rd April |  | 1st May | 8th May | 8th May |  | 30th Jan | 6th Feb | 13th Feb | 20th Feb | 6th March | 13th March | 20th March | 27th march | 3rd April |  | 1st May | 8th May | 8th May
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | EASTER | Week 10 | Week 11 | Week 12 |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | EASTER | Week 10 | Week 11 | Week 12
Player | [13 empty] | Player | [5 empty] | Code Review / Beta |  |  |  |  | Playtest bugfixing | Testing For Release
z | [13 empty] | Movement | bar: Week 2 to Week 5
Moving | [13 empty] | Jumping | bar: Week 8 to Week 9
Attack
Death
Pickup Collectable
Enemies | [13 empty] | Enemies
Enemy 1 - Still | [13 empty] | Enemy Movement | bar: Week 4
Enemy 2 - Floor moving | [13 empty] | Enemy death | bar: Week 5
Enemy 3 - Flying | [13 empty] | Drop collectable | bar: Week 6 to Week 7
Pickups | [13 empty] | World | bar: Week 6 to Week 9
Money | [13 empty] | Audio | bar: Week 8 to Week 9
Chest | [13 empty] | Respawn | bar: Week 8 to Week 9
Player Health Icon | [13 empty] | Teleport | bar: Week 6 to Week 7
Tiles / Decals | [13 empty] | Camera | bar: Week 2 to Week 7
World 1 | [13 empty] | Save | bar: Week 2 to Week 3
World 2 | [13 empty] | World changes | bar: Week 4 to Week 5
World 3 | [13 empty] | Rotate Gravity | bar: Week 6 to Week 7
Chests
Map Design | [13 empty] | Player Animation | bar: Week 3 to Week 9
World 1 | [13 empty] | Enemy Animation | bar: Week 3 to Week 4
World 2 | [13 empty] | Artifact Animaton | bar: Week 5 to Week 6
World 3 | [13 empty] | World Animation | bar: Week 7 to Week 8
UI | [13 empty] | UI | bar: Week 8 to Week 9
Resume | [13 empty] | Pause | bar: Week 8 to Week 9
Exit | [13 empty] | Reset | bar: Week 8 to Week 9
Start | [13 empty] | Main Menu | bar: Week 8 to Week 9
Reset | [13 empty] | Win | bar: Week 8 to Week 9
Loading / Fade
Boss | Week 1: < Out Of Scope > |  |  |  |  | Boss | < Out Of Scope >
Stationary | [13 empty] | Movement
Moving | [13 empty] | Attacks
Attacking | [13 empty] | HP / Death
AUDIO
Player death sfx
Jump sfx
attack sfx
bounce attack sfx
Enemy hit
Enemy death
Enemy attack
Boss
BGM
Move sound
Attack sount
Level 1
BGM
Level 2
BGM
Level 3
BGM
Pickups:
Money
Chest Open
Player lose / gain health
click UI element
Exit game | [13 empty] | AUDIO
Begin | [13 empty] | Player death sfx
Reset | [13 empty] | Jump sfx
CODE | [13 empty] | attack sfx
Player | Week 6: Code Review / Beta |  | Playtest bugfixing | Testing For Release |  | bounce attack sfx
Movement | bar: Week 1 to Week 2
Jumping | [13 empty] | Enemy hit | bar: Week 2 to Week 3
Attack | [13 empty] | Enemy death | bar: Week 3
Death | [13 empty] | Enemy attack
Pickup Collectable | bar: Week 5 to Week 7
Boss
Enemy | [13 empty] | BGM | bar: Week 4
Enemy Movement | [13 empty] | Move sound | bar: Week 5 to Week 6
Enemy death | [13 empty] | Attack sount | bar: Week 5 to Week 6
Drop collectable | bar: Week 5 to Week 6
Level 1
World | [13 empty] | BGM
Audio | bar: Week 3 to Week 6
Respawn
Teleport | [13 empty] | Level 2 | bar: Week 1
Camera | [13 empty] | BGM | bar: Week 1; Week 6 to Week 7
Save | bar: Week 2 to Week 3; Week 8
World changes
Rotate Gravity | [13 empty] | Level 3 | bar: Week 6 to Week 7
Chests | [13 empty] | BGM | bar: Week 8
UI | [13 empty] | Pickups:
Pause | [13 empty] | Money | bar: Week 1
Reset | [13 empty] | Chest Open | bar: Week 3; Week 6 to Week 7
Main Menu | [13 empty] | Player lose / gain health | bar: Week 8 to Week 9
Win | bar: Week 9
Loading | [13 empty] | click UI element | bar: Week 8
Fade in | bar: Week 8
Exit game
Begin
Reset

## ASSET LIST
Visual | Audio | Code
Player |  | Player
Standing |  | Movement
Moving |  | Jumping
attack side |  | Attack
attack down |  | Death
Enemy 1 - Still |  | Enemy Movement
Enemy 2 - Floor moving |  | Enemy death
Enemy 3 - Flying
World:
Boss |  | Audio
Stationary |  | Respawn
Moving |  | Teleport
Attacking |  | Rotate Gravity
Save
Level 1 |  | World changes
Tiles |  | Camera
Decals
Level 2
Tiles
Decals
Level 3
Tiles
Decals
Money
Chest
Player Health Icon
UI
Resume
Exit
Start
Reset